## Sheet1
id | Primary Text | Artifact Type | Supplier_1 Status | OEM_1 Status | Stakeholder Domain | Link:Link To (>) | OEM_1 Reason | Supplier_1 Comment | isHeading | parentBinding | module
64599 | Security and Protection | Heading | [6 empty] | true | 64498 | 64440
64600 | This chapter does not represent a complete list of the security requirement, but forms the basis on which security-features of functions are defined in other specification parts. In this respect, the contractor is required to analyze and evaluate the complete requirement specifications with regard to security. The individual subchapters describe the security aspect and not the whole function. If further requests are made to the security in other parts of the requirement specifications, they apply. However, the requirements from this chapter shall not be undershot. | Requirement | agreed | accepted | PM | 154533: MGU List {LINK id=130932.154533 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_pORko-8QEe2Aa7te25qZeg} 134735: Requirements Elicitation of customer security modules (63339: Debugging Interfaces Security,63360: Flashware Encryption, 63401: HSM Requirements, 63605: IMU Security, 63755: Penetration Testing, 64045: Rollback Protection, 63876: Secure Boot, 64039: Securi {LINK id=130932.134735 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_dtnZpLzjEe2JSfLsA23oZA} |  |  | false | 64599 | 64440
64601 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | agreed | accepted | PM | 154533: MGU List {LINK id=130932.154533 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_pORko-8QEe2Aa7te25qZeg} | 2021-12-03 Herrmann/Poellny: MSS10902 & MSS10903 are applicable for the BR223MOPF/BR297MOPF & BR296MOPF // see above | To be clarified by Daimler. The MSS 10902 and MSS 10903 have been mentioned as No Successor at the time of Withdrawal, meaning these documents are no longer relevant and valid? | false | 64599 | 64440
64602 | In the case of a residual bus simulation, a SecOC calculation for selected signals may be required. | Requirement | agreed | accepted | Test | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_0WGegK3yEe2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64599 | 64440
64603 | Appropriate measures must be taken by the contractor to protect the provided crypto material. These are: - Implementation of a security concept including Security Incident Management by the contractor and inspection by the contacting authority. - Need to Know Principle (only employees who need the provided information directly for the fulfillment of a specific task get access) - Training and awareness-raising activities for employees - Rules for using client's Security Tools - Rules for registering users in client's Directory | Requirement | agreed | accepted | PM | 130932.155490: Security tools and process handling {LINK id=130932.155490 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_UXzHgQFEEe6S65toj012sg} 130932.155441: Data Protection and information Security Training {LINK id=130932.155441 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_FoQd4wBoEe6S65toj012sg} |  |  | false | 64599 | 64440
64604 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_AlW6cLH1Ee2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_uJ9dsK00Ee2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_Ked1I601Ee2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_HiDm0LH1Ee2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_vqrCgK00Ee2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_yShV4K0xEe2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64599 | 64440
64605 | Referenced Documents | Heading | [6 empty] | true | 64599 | 64440
64606 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 154696: MSS 10796 ¦ Standard Security Specification ¦ 05.2020 ¦ TBD {LINK id=154696 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_GYYDN_DFEe2Aa7te25qZeg} | 2022-06-23 CH: CR003: change to SSA3.x and Autosar Ferrum with SW1.6, please set Req. to "accepted" 2022-07-22 CH: accepted | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. Old Comments: Changed to Clarify as the SSA version is in clarification. Agreed based on Change Request: 2798589: MMP2.11 MB - CR003 - SSA3 Integration (Ferrum) | false | 64605 | 64440
64607 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted |  | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_0unzcf0-EeypboQq9iL2pA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_DOEZ08S7Eey3i-0XVUovJw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_eoTjkdhSEeypoOqndP1Hvw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: Setting to partly agreed to better handle the process for requirement engineering. Not every requirement in the Flash loader specification is applicable to the IMU. The agreed requirements will be implemented. | false | 64605 | 64440
64607 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted |  | 154698: MSS 10809 ¦ Standard Flashloader Specification ¦ 10.2020 ¦ TBD {LINK id=154698 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_HVPUF_DFEe2Aa7te25qZeg} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: Setting to partly agreed to better handle the process for requirement engineering. Not every requirement in the Flash loader specification is applicable to the IMU. The agreed requirements will be implemented. | false | 64605 | 64440
64608 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 154699: MSS 10815 ¦ Standard Security Architecture - Implementation Specification ¦ 06.2021¦ TBD {LINK id=154699 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_HVPUFvDFEe2Aa7te25qZeg} | 2022-06-23 CH: CR003: change to SSA3.x and Autosar Ferrum with SW1.6, please set Req. to "accepted" 2022-07-22 CH: accepted 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. Old Comments: Changed to Clarify as the SSA version is in clarification. Agreed based on Change Request: 2798589: MMP2.11 MB - CR003 - SSA3 Integration (Ferrum) | false | 64605 | 64440
64609 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted |  | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_59imcKxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. | false | 64605 | 64440
64610 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 130932.176749: Security Information MGUs {LINK id=130932.176749 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_THHJM2EfEe61b-sWvW5_gg} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. | false | 64605 | 64440
64609 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted |  | 154701: MSS 10820 ¦ Requirement Specification for SHA512 and Ed25519ph ¦ TBD ¦ TBD {LINK id=154701 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_LRfuRvDFEe2Aa7te25qZeg} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. | false | 64605 | 64440
64610 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 154702: MSS 10824 ¦ Requirement Specification for Certificate Structure ¦ 03.2021¦ TBD {LINK id=154702 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_LRfuR_DFEe2Aa7te25qZeg} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. | false | 64605 | 64440
64611 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 154703: MSS 10866 ¦ 2017-03-09 Specification for Key-Format CCCv2 ¦ 07.2017 ¦ TBD {LINK id=154703 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_L_5sYPDFEe2Aa7te25qZeg} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. | false | 64605 | 64440
64612 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 154704: MSS 10872 ¦ MSS-10872 Specification for ZIP-CertificateBag V1.0 ¦ 07.2017¦ TBD {LINK id=154704 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_L_5sYfDFEe2Aa7te25qZeg} | 2023-06-27 oberlin: accepted and discussed in advanced the status change with supplier | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. | false | 64605 | 64440
64613 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 154725: MSS 10902 ¦ ¦ TBD ¦ TBD {LINK id=154725 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_nufzBvDIEe2Aa7te25qZeg} | 2021-12-03 Herrmann/Poellny: MSS10902 & MSS10903 are applicable for the BR223MOPF/BR297MOPF & BR296MOPF // see above 2023-06-27 oberlin: accepted | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. Old Comments: To be clarified by Daimler. The MSS 10902 and MSS 10903 have been mentioned as No Successor at the time of Withdrawal, meaning these documents are no longer relevant and valid? | false | 64605 | 64440
64614 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 154726: MSS 10903 ¦ ¦ TBD ¦ TBD {LINK id=154726 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_oac6FvDIEe2Aa7te25qZeg} | 2021-12-03 Herrmann/Poellny: MSS10902 & MSS10903 are applicable for the BR223MOPF/BR297MOPF & BR296MOPF // see above 2023-06-27 oberlin: accepted | 28.03.23 Mithun Changed to Partly Agreed: The SSA 3.x will be integrated. Setting to partly agreed to better handle the process for requirement engineering as RB is not implementing the components of SSA, but integrating the SSA components. Old Comments: To be clarified by Daimler. The MSS 10902 and MSS 10903 have been mentioned as No Successor at the time of Withdrawal, meaning these documents are no longer relevant and valid? | false | 64605 | 64440
64615 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | not agreed | accepted |  |  | accepted | Ethernet is not supported in the IMU project | false | 64605 | 64440
64616 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | agreed | accepted | PM | 154533: MGU List {LINK id=130932.154533 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_pORko-8QEe2Aa7te25qZeg} |  |  | false | 64605 | 64440
64617 | {LINK title="[MSS 10816]" uri=https://mbse.i.mercedes-benz.com/rm1/resources/CA_c1c59d384db049ffbb462f5e9dba4fbd}- Standard Security Architecture for AUTOSAR Adaptive - Implementation Specification | Requirement | not agreed | accepted |  |  | accepted | IMU Shall support classic Autosar and not adaptive Autosar. | false | 64605 | 64440
64618 | {LINK title="[MSS 10799]" uri=https://mbse.i.mercedes-benz.com/rm1/resources/CA_05852b8eb9c64c2ca9c900495b3d3bb2} - Standard Security Architecture for AUTOSAR Adaptive | Requirement | not agreed | accepted |  |  | accepted | IMU Shall support classic Autosar and not adaptive Autosar. | false | 64605 | 64440
64617 | {LINK title="[MSS 10816]" uri=https://mbse.i.mercedes-benz.com/rm1/resources/CA_c1c59d384db049ffbb462f5e9dba4fbd}- Standard Security Architecture for AUTOSAR Adaptive - Implementation Specification | Requirement | not agreed | accepted |  |  | accepted | IMU Shall support classic Autosar and not adaptive Autosar. | false | 64605 | 64440
64618 | {LINK title="[MSS 10799]" uri=https://mbse.i.mercedes-benz.com/rm1/resources/CA_05852b8eb9c64c2ca9c900495b3d3bb2} - Standard Security Architecture for AUTOSAR Adaptive | Requirement | not agreed | accepted |  |  | accepted | IMU Shall support classic Autosar and not adaptive Autosar. | false | 64605 | 64440
64619 | The contractor shall take into consideration any applicable standard, and/or regulation, and/or legislation, even in draft state, if it is foreseable to be applicable at the start of production or at the start of sale. | Requirement | partly agreed | accepted | PM | 145495: Certificate XC-DX Process Library Cybersecurity Management System according to ISO/SAE 21434 ¦ {LINK id=130932.145495 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_9zMO7M6-Ee2RxeJKOft6lQ} | 220422ub: accepted 2021-12-07 CH: DIA 8 weeks after official project allocation | To be discussed in DIA. We can only consider released version of standards, Legislation, Regulations etc. Design Freeze to be considered. In case of change in the standard during development or in series, it needs to be handled as a CR. | false | 64605 | 64440
64620 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | partly agreed | accepted | PM | 145497: Certificate DIN EN ISO/IEC 27001:2017 ¦ {LINK id=130932.145497 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_cuHO8M6_Ee2RxeJKOft6lQ} | 220422ub: accepted 2021-12-07 CH: DIA 8 weeks after official project allocation | To be discussed in DIA. We can only consider released version of standards, Legislation, Regulations etc. Design Freeze to be considered. In case of change in the standard during development or in series, it needs to be handled as a CR. | false | 64605 | 64440
64621 | General Basica | Heading | [6 empty] | true | 64599 | 64440
64622 | Flashware protection shall be implemented according to the applicable reference documents [MSS 10809]. | Requirement | agreed | accepted | PM | 154533: MGU List {LINK id=130932.154533 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_pORko-8QEe2Aa7te25qZeg} |  |  | false | 64621 | 64440
64623 | The component shall provide security mechanisms to prevent remote attacks (e.g. through remote interfaces). | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_34U1IaxGEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64621 | 64440
64624 | The component shall provide mechanisms, which prevent an attacker from unauthorized manipulation of software and/or data of the component. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_dBaHcLTVEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64621 | 64440
64625 | The component shall provide mechanisms to protect the integrity of the software and data of the system and its components. The behavior in the case of a detected manipulation shall be coordinated with the client. In case of a multiprocessor system, this mechanism must be examined individually for each processor / memory. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI__1WHUKxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | accepted | System behaviour in case of Manipulation detection on one microcontroller to be decided. | false | 64621 | 64440
64626 | The component shall not store user private data unless the confidentiality of the data is protected and the user consent was given. In any case private data storage shall be approved by the customer. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} | 2021-12-03 Herrmann/Poellny: please set requirement to accepted. | To be clarified by Daimler. Which Private data or user data is to be stored or processed by the IMU? 2022-01-04: Mithun Status set to Agreed. Reason for the question on Type of Data is to comply to the Data Protection Check as per RB Security Engineering Process. Clarification is still required. | false | 64621 | 64440
64627 | The component shall only contain the function described in the requirement specifications. | Requirement | agreed | accepted | PM | 153663: Technical Customer Documentation {LINK id=130932.153663 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_0auLAumWEe2Bvr_BtPnMGg} | 2021-12-03 Herrmann/Poellny: please set requirement to "accepted", functions will be clarified during development. | To be clarified by Daimler. Where do we find the requirements for the function? 2022-01-04: Mithun As per Comment from Daimler, Functions will be clarified during Development. | false | 64621 | 64440
64628 | A security solution for the component shall be developed by the contractor and approved by the client. | Requirement | agreed | accepted | PM | 153658: SW Feature Implementation Plan (FIP) {LINK id=130932.153658 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_mVdn4-mTEe2Bvr_BtPnMGg} | accepted | Implemented Security solution is based on SSA and additional solutions will be communicated to the client. | false | 64621 | 64440
64629 | Components having increased security needs, shall additional reserve 150 kB ROM and 32 kB RAM. Rationale: For future cryptographic updates. | Requirement | partly agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_PS4IRMz6EeypoOqndP1Hvw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2021-12-07 CH: accepted? | Future changes related to cryptography will mean a change in existing software. Existing Cryptographic software will be replaced with new cryptographic updates. Sufficient memory will be reserved for HSM. However such scenarios are to be clarified. | false | 64621 | 64440
64630 | Components having increased security needs, shall reserve a 192 kB ROM block for flashbootloader. Rationale: For future cryotographic updates of flashbootloader. | Requirement | partly agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_PS4IRMz6EeypoOqndP1Hvw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2021-12-07 CH: accepted? | Future changes related to flash loader will mean a change in existing software. Existing flash loader software will be replaced with new flash loader updates. Sufficient memory will be reserved for flash loader. However such scenarios are to be clarified. | false | 64621 | 64440
64631 | Components having increased security needs, shall have a minimum of 192 kB RAM for flashware signature verification while flash rom update is active. An additional amount of ram for extra cryptographic functions shall be taken into account. Rationale: For future cryotographic updates of flashbootloader. | Requirement | partly agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_bQPAE7_eEeyUhN9EjSfyyA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2021-12-07 CH: accepted? | Future changes to the memory need to be discussed. | false | 64621 | 64440
64632 | Hardware Security | Heading | [6 empty] | true | 64599 | 64440
64633 | Internal parameters which relate to the condition of the system with regard to security shall not be manipulated via diagnosis or debug mechanism. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_UlSu4MS8Eey3i-0XVUovJw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64632 | 64440
64634 | Sensitive information shall be protected against unauthorized use. Examples of sensitive information are cryptographic keys and passwords. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_UlSu4MS8Eey3i-0XVUovJw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64632 | 64440
64635 | Hardware Security Module | Heading | [6 empty] | true | 64599 | 64440
64636 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64635 | 64440
64637 | If the microcontroller has a HSM, the following Requirements are mandatory: STLH-7167 to 7171) as well as the Section „Asymmetric Crypto“ (STLH-7173) resp. (STM-1317006). | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64635 | 64440
64638 | All cryptograpic operations which use keys stored inside the HSM shall be implemented inside the HSM. Any exceptions shall be approved by the client in written form. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64635 | 64440
64639 | Private/symmetric key material stored in the HSM shall not be exported or exportable from the HSM during runtime. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/web#action=com.ibm.rdm.web.pages.showArtifactPage&amp;artifactURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fresources%2FBI_wtCwwPkrEe2QFYUUNHBc3A&amp;vvc.configuration=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ&amp;componentURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Frm-projects%2F_OKLh9HQHEeWQoekIYfM7mg%2Fcomponents%2F_g_sDUA5aEeayWuF486H6EQ} |  |  | false | 64635 | 64440
64640 | Unauthorized access to the HSMs functions and data shall be protected by the HSM, e.g. using access control. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/web#action=com.ibm.rdm.web.pages.showArtifactPage&amp;artifactURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fresources%2FBI_UxKVAAtQEe6CH98ykT4lhQ&amp;vvc.configuration=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ&amp;componentURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Frm-projects%2F_OKLh9HQHEeWQoekIYfM7mg%2Fcomponents%2F_g_sDUA5aEeayWuF486H6EQ} |  |  | false | 64635 | 64440
64641 | The HSM shall povide secured storage mechanism that is resilient to physical attacks. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_UlSu4MS8Eey3i-0XVUovJw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64635 | 64440
64642 | The HSM shall provide means to perform crypto related operations using internally stored keys on data that is provided via an external interface. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64635 | 64440
64643 | Supported Crypto Primitives and Functions | Heading | [6 empty] | true | 64599 | 64440
64644 | Asymmetric Crypto | Heading | [6 empty] | true | 64643 | 64440
64645 | If asymmetric key material is generated during runtime, this shall be done in an HSM. Any exceptions shall be approved by the client in written form. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/web#action=com.ibm.rdm.web.pages.showArtifactPage&amp;artifactURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fresources%2FBI_wtCwwPkrEe2QFYUUNHBc3A&amp;vvc.configuration=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ&amp;componentURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Frm-projects%2F_OKLh9HQHEeWQoekIYfM7mg%2Fcomponents%2F_g_sDUA5aEeayWuF486H6EQ} |  |  | false | 64644 | 64440
64646 | The HSM shall support crypto primitives and algorithms as specified by reference documents. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64644 | 64440
64647 | The HSM shall provide random number generators as specified by reference documents. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_E45kgMoMEeypoOqndP1Hvw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64644 | 64440
64648 | The HSM shall provide sufficient storage capacity as speficied by refernce documentation and specific component requirements. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_bQPAE7_eEeyUhN9EjSfyyA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64644 | 64440
64649 | Debug Interfaces | Heading | [6 empty] | true | 64643 | 64440
64650 | All low-level debug interfaces (e.g. JTAG, SWD, XCP, serial) shall be protected by a strong authentication mechanism that utilizes a key or password that provides a security strength of at least 112 bit symmetric equivalent. If the protection is not feasible for a specific interface an alternative solution shall be discussed and approved by the client. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_8rI1I6xMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64649 | 64440
64651 | All high-level debug interfaces (e.g. adb shells, CLIs, GUIs) shall be protected by a strong authentication mechanism that utilizes a key or password that provides a security strength of at least 128 bit symmetric equivalent. If the protection is not feasible for a specific interface an alternative solution shall be discussed and approved by the client. | Requirement | not agreed | accepted |  |  | 211119ub | High Level Debug interfaces such as adb shells, GUIs are not relevant for the IMU unit. | false | 64649 | 64440
64652 | CRRRS4242E This content cannot be exported because it contains malformed text or hyperlinks. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_8rI1I6xMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64649 | 64440
64653 | Miscellaneous Secure Hardware Requirements | Heading | [6 empty] | true | 64643 | 64440
64654 | Hardware Security requirements shall be implemented as specified by referenced documents. | Requirement | agreed | accepted | PM | 134735: Requirements Elicitation of customer security modules (63339: Debugging Interfaces Security,63360: Flashware Encryption, 63401: HSM Requirements, 63605: IMU Security, 63755: Penetration Testing, 64045: Rollback Protection, 63876: Secure Boot, 64039: Securi {LINK id=130932.134735 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_dtnZpLzjEe2JSfLsA23oZA} | why to clarify? @UB: Link doesn't work --> link deleted 2022-06-23 CH: CR003: change to SSA3.x and Autosar Ferrum with SW1.6, please set Req. to "accepted" 2022-07-22 CH: accepted | To be clarified by Daimler: Link is not working. Reference Document numbers to be specified. 03.05.2022: Mithun After Clarification with Mikhail, the Documents mentioned in this requirement are the documents in section 1.3.6.1 Referenced Documents. Partly agreed for now due to clarification regarding the SSA version and the corresponding MSS documents. 11.07.2022: Agreed based on Change Request: 2798589: MMP2.11 MB - CR003 - SSA3 Integration (Ferrum) | false | 64653 | 64440
64655 | Operating System and application hardening | Heading | [6 empty] | true | 64599 | 64440
64656 | Operating System and application hardening shall be done according to the referenced doucments and according to the component specific requirements | Requirement | partly agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_FT8_7VkmEe6HtI_Dta151g?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2022-02-07: Cubas is a mixture of Autosar Versions 4.2 and 4.3 // joint development needs to be aligned later on. 2021-12-03 Herrmann/Poellny: We assume that for Cubas no Document is available. suggested approach ist to do OS hardening in joined manner during the project. | To be clarified by Daimler. Reference Document number to be specified. OS hardening is in general a microprocessor topic and may not be directly relevant for the IMU ECU. Joint Development for OS Hardening to be discussed again. | false | 64655 | 64440
64657 | Processes and applications shall be limited to the least possible rights required to fulfill their respective use-case. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64658 | Processes shall be prevented from manipulating or influencing other processes by suitable mechanisms. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64659 | The operating system shall be hardened if applicable according to the specific hardening requirements suggested by the contractor and approved by the client. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64660 | The security mechanisms provided by the hardware (e.g. NX bit) shall be activated in the operating system. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64661 | Access rights shall be defined according to the least privilege prinicple. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/web#action=com.ibm.rdm.web.pages.showArtifactPage&amp;artifactURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fresources%2FBI_UxKVAAtQEe6CH98ykT4lhQ&amp;vvc.configuration=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ&amp;componentURI=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Frm-projects%2F_OKLh9HQHEeWQoekIYfM7mg%2Fcomponents%2F_g_sDUA5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64662 | If Address Space Layout Randomization (ASLR) is supported by the operating system, this shall be used. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64663 | All userspace binaries shall be compiled as Position Independent Executables (PIE) to support ASLR. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64664 | Features of the operating system which are not requiered shall be deactivated. This applies particularly to debug features. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64665 | Drivers which are not required shall be deactivated, and if technically possible, deleted from the operating system. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64666 | Driver features which are not requiered shall be deactivated, if technically possible, or deleted from driver. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64667 | If a multi user operating system is used, applications and services shall be distribute meaningfully, to systemusers with restricted rights. | Requirement | not agreed | accepted |  |  | 211119ub | We do not use a multiuser OS in the IMU | false | 64655 | 64440
64668 | Information on the exact configuration of the operating system must be removed from the software release if technically feasible. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64669 | Login credentials shall be unique and individual. Exceptions to this requirements shall be approved by the customer. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64670 | If the component manages sessions, the period of validity of the session shall be selected as small as possible. | Requirement | not agreed | accepted |  |  | 211119ub | Is not relevant for the IMU ECU as it is not having a POSIX based OS. | false | 64655 | 64440
64671 | Third-party software that contains publicly-known, unfixed vulnerabilities shall not be used in the component. | Requirement | agreed | accepted | PM | 158978: FOSS Scan results {LINK id=130932.158978 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_qTyiARDMEe6kHpr-xdouxA} |  |  | false | 64655 | 64440
64672 | The contractor shall use the most up-to-date software components and OS versions unless otherwise approved by the client. | Requirement | agreed | accepted | PM | 154093: Security Bill of Materials {LINK id=130932.154093 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_-EJFkO12Ee2Aa7te25qZeg} 158978: FOSS Scan results {LINK id=130932.158978 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_qTyiARDMEe6kHpr-xdouxA} |  |  | false | 64655 | 64440
64673 | Production grade software shall not contain any debug symbols and debug information. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64674 | Software components which are only created for debuging-, developing- or testing-reasons shall be removed in production grade software releases. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64675 | The software components shall utilize the security mechanisms provided by the compiler and/or runtime environment. | Requirement | agreed | accepted | SW,Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI__VgvsL_fEeyUhN9EjSfyyA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_fJgHOVuFEe6wQOzOaO6ZtQ?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64676 | The supplier shall use compiler options to protect against buffer overflows if applicable. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI__VgvsL_fEeyUhN9EjSfyyA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 220414ub: accepted 2021-12-13 CH: with regard to your comment: why just partly agreed? | If the feature is supported in the compiler, it can be activated. | false | 64655 | 64440
64677 | The application shall use mechanisms to prevent code injections. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_eoTjkdhSEeypoOqndP1Hvw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_34U1IaxGEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ZUOx8KxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_GMYXU6xMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_dBaHcLTVEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2021-12-03 Herrmann/Poellny: Code injection as in the unauthorized (not signed) altering, addition or deletion of program code in software. The requirement refers to all types of code injection. | To be clarified by Daimler. What is the rationale of the term code injection? Can we consider delta flashing, if supported as code injection? 2022-01-04: Mithun Agreed with the provided Clarification. | false | 64655 | 64440
64678 | Software shall be protected against reverse engineering. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_8rI1I6xMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ha7lMK5uEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_6QFLIMS6Eey3i-0XVUovJw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64679 | If key material is not stored in a HSM, unencrypted key material shall only be held in RAM or file system for the shortest possible time required to perform crypto operations with it. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64680 | If key material is not stored in a HSM, the key material is to be stored and processed in a Trusted Execution Environment (TEE), if this is technically possible and the hardware platform used provides a TEE. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64655 | 64440
64681 | Diagnosis | Heading | [6 empty] | true | 64599 | 64440
64682 | Diagnosis functions shall not disclose any information beyond the legally required dimension without any previous authentication. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_34U1IaxGEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_GMYXU6xMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64681 | 64440
64683 | The component shall not contain any undocumented diagnostic services. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ha7lMK5uEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64681 | 64440
64684 | Diagnosis services created by the contractor for their own use (e.g. Production) shall be disclosed to the client and require explicit approval by the client. | Requirement | agreed | accepted | PM | 155223: RB Diagnostics presence aligned. {LINK id=155223 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_iq4ukPrhEe2S65toj012sg} |  |  | false | 64681 | 64440
64685 | While driving diagnostic services must be reduced to the statutory minimum. See DDS, DRECU Chapter Security. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_v3YjERfqEe21moPx3y3GWg?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_jroXgJY7EeyDtsYIjeEGvg?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64681 | 64440
64686 | Communication channels | Heading | [6 empty] | true | 64599 | 64440
64687 | The component shall only provide access interfaces which are required by relevant specifications. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ha7lMK5uEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64688 | The component shall provide mechanisms to establish and maintain secure communication channels to external services. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_59imcKxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64689 | Mutual authentication shall be used to setup secure communication channels. | Requirement | agreed | accepted | SW,Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_34U1IaxGEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_59imcKxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64690 | Mutual authentication shall be used for wireless interfaces. | Requirement | not agreed | accepted |  |  | accepted | IMU Does not support wireless communication or interfaces. | false | 64686 | 64440
64691 | Communication interfaces and their drivers are to be limited to the feature and protocol required for operating the control unit. | Requirement | agreed | accepted | SW | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_xc_eUNgVEeypoOqndP1Hvw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64692 | Communication interfaces that are not used in a certain control unit configuration or operating state shall be switched off during operation. This applies especially to radio interfaces. | Requirement | not agreed | accepted |  |  | ub | 2023-11-20 Rogge, Mithun: IMU has no radio interfaces and therefore not applicable. We do not use other interfaces such as Ethernet and LIN; or flexray. the PCB has no connections for such interfaces. | false | 64686 | 64440
64693 | Communication interfaces that are generally not used in a certain hardware variant are to be deactivated in a irreversibly hardware manner (e.g. due to missing contact on the PCB, short circuit, fuses, etc.). | Requirement | not agreed | accepted | SYS |  | accepted | 2023-04-13 Rogge, Kossira: No HW variants, not applicable | false | 64686 | 64440
64694 | The component shall provide mechanisms to enforce the separation of different in-car networks. | Requirement | not agreed | accepted |  |  | 2022-02-03 CH: accepted, as not relevant for IMU ECU? | Domain Separation is under the vehicle network architecture in a CAN network and cannot be provided by the IMU Component independently. 2022-01-04: Mithun Which Mechanism is expected from the IMU Component to enforce separation of different in - car Networks? | false | 64686 | 64440
64695 | The component shall provide mechanisms to restrict the communication between in-car and external connected networks only to the necessary content and communication patterns. | Requirement | partly agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ha7lMK5uEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2021-12-07 CH: accepted? | The IMU shall only provide necessary communication agreed and any additional mechanisms need to be agreed upon. 2022-01-04: Mithun The Component shall only implement communication channels which are defined and necessary. | false | 64686 | 64440
64696 | The component shall reject faulty or unexpected messages, packets and data. The function of the components shall not be influenced. | Requirement | agreed | accepted | SW,Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_59imcKxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64697 | The component shall perform input validation. | Requirement | agreed | accepted |  | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_eCdRYLd2Ee26jdhA1fMq8g?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64698 | The component shall correctly code all output signal ("output encoding"). | Requirement | agreed | accepted |  | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_1vbnwM-tEeypoOqndP1Hvw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64699 | The functionality implemented by all interfaces shall be minimal, i.e. the interfaces shall only offer the explicitly specified functionality. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ha7lMK5uEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64700 | Remote interfaces shall be isolated from vehicle internal bus. | Requirement | not agreed | accepted |  |  | 220422ub: accepted 2021-12-07 CH: accepted? | 2023-03-30 Rogge: Requirment is for vehicle bus, no requirement for IMU. RB can not verify this. Vehicle Network is under the scope of the network architecture and is not defined by the IMU Component. The IMU Component is connected to the Vehicle Bus by CAN interface. 2022-01-04: Mithun Definition of Remote interface has to be clarified. | false | 64686 | 64440
64701 | The component shall provide protection against replay attacks on its interfaces. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_59imcKxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64702 | Consumer electornic interfaces which are not customer accessible, shall be secured with cryptographicaly strong passwords. Default passwords are not allowed. | Requirement | not agreed | accepted |  |  | 211119ub | Not applicable for the IMU ECU | false | 64686 | 64440
64703 | Credentials shall be transferred confidentially (by means of encryption) on the vehicle bus. | Requirement | not agreed | accepted |  |  | 2022-02-07: check with O.Poellny if relevant for IMU ECU. RB: CMAC, Authentication certificates and signatures will be not considered as credentials. 2022-09-21:oberlin set it to accepted as it was already accepted by the previus SA Mikhail Sharapov and we don't have any credentials | IMU does not transfer credentials on the Vehicle Bus | false | 64686 | 64440
64704 | Secured interfaces shall be protected against brute-force-attacks. | Requirement | agreed | accepted | SW,Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_59imcKxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 2021-12-07 CH: accepted | Brute force protection needs to be available as a feature from SSA side. | false | 64686 | 64440
64705 | Messages routing mechanisms shall be implemented by using the "whitelist" approach (with "default-deny"). | Requirement | not agreed | accepted |  |  | 220810ub: accepted following comment of Mikhail 2022-02-07: MB - internal clarification needed. | To be clarified by Daimler. Does this imply that the first IMU shall verify the incoming PDUs before routing? 03.05.2022: After clarification with Mikhail, the whitelisting approach is not applicable to the IMU as the IMU shall only be implemented as per the NCD and defined messages shall be handled by the IMU. | false | 64686 | 64440
64706 | During the implementation of standard protocols, it shall be ensured, that no "downgrade" (e.g. Cipher-downgrade) is possible, i.e. the security mechanisms cannot be lowered by the level specified by the client. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_DOEZ08S7Eey3i-0XVUovJw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64686 | 64440
64707 | Cryptographic and security mechanisms known as vulnerable and/or weak shall not be used. This also aplies to the mechanisms which are expected to be vulnerable and/or weak by the start of production and/or start of sales. | Requirement | agreed | accepted | PM | 145495: Certificate XC-DX Process Library Cybersecurity Management System according to ISO/SAE 21434 ¦ {LINK id=130932.145495 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_9zMO7M6-Ee2RxeJKOft6lQ} |  |  | false | 64686 | 64440
64708 | Every component which includes a cryptographic routine, shall have a means to update or replace the underlying algorithm. Rationale: Once a cryptographic algorithm gets broken it has to be updated or replaced to a stronger one. | Requirement | partly agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_DOEZ08S7Eey3i-0XVUovJw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ZUOx8KxMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 220414ub: accepted 2021-12-07 CH: accepted | Such events will be discussed further. To clarify regarding verification criteria of the requirement. | false | 64686 | 64440
64709 | Logging/Monitoring | Heading | [6 empty] | true | 64599 | 64440
64710 | Credentials or other security parameters shall not be logged. | Requirement | agreed | accepted | PM | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_7GtN86xMEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64709 | 64440
64711 | The contractor should make further suggestions for events that also be held in the security log. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} | 220414ub: accepted 2021-12-07 CH: accepted | Such events will be discussed further. | false | 64709 | 64440
64712 | Debug information (in whatever form) that reveals any detailed information regarding components functionality shall not be logged in the production grade device. Any exceptions shall be approved by the client in the written form. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | accepted | Does Failure log classify under Debug data? | false | 64709 | 64440
64713 | In the course of development, the contractor and the client shall define when and in which form events shall sent to the Event Collector (directly when the event occurs, aggregated, cyclical, …). | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} | 211119ub | To be discussed during the course of development. | false | 64709 | 64440
64714 | Debugging | Heading | [6 empty] | true | 64599 | 64440
64715 | The production grade component shall not contain any unprotected maintenance interfaces . | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ha7lMK5uEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64714 | 64440
64716 | Random numbers | Heading | [6 empty] | true | 64599 | 64440
64717 | 3rd-Party software | Heading | [6 empty] | true | 64599 | 64440
64718 | The contractor is obliged to check the origin of software, libraries or source code, from third parties and to obtain via secure channels. If cryptographic signature are used for the software components, they must be checked. | Requirement | partly agreed | accepted | PM | 154093: Security Bill of Materials {LINK id=130932.154093 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_-EJFkO12Ee2Aa7te25qZeg} | 2022-02-07: if there won't be any 3rd party sw in the future - we will accept the "partly agreed" | To be clarified by Daimler. Is this requirement applicable even for the SSA? No other Third Party SW is used in IMU. | false | 64717 | 64440
64719 | The contractor shall integrate regular updates of the 3rd-party software. | Requirement | partly agreed | accepted | PM | 154093: Security Bill of Materials {LINK id=130932.154093 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_-EJFkO12Ee2Aa7te25qZeg} | accepted | To be clarified by Daimler. Is this requirement applicable even for the SSA? | false | 64717 | 64440
64720 | The contractor shall ensure that all 3rd-party software is free of any known vulnerability and/or backdoors. | Requirement | partly agreed | accepted | PM | 154093: Security Bill of Materials {LINK id=130932.154093 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_-EJFkO12Ee2Aa7te25qZeg} | accepted | To be clarified by Daimler. Is this requirement applicable even for the SSA? | false | 64717 | 64440
64721 | The contractor shall disclose to the client all used 3rd-party software software. | Requirement | agreed | accepted | PM | 154093: Security Bill of Materials {LINK id=130932.154093 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_-EJFkO12Ee2Aa7te25qZeg} |  |  | false | 64717 | 64440
64722 | The contractor shall disclose the configuration of the operating system cores (kernel) to the client. | Requirement | partly agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} | 220414ub: accepted | A view on site can be provided if required. To be discussed further, regarding required information. The information regarding scheduling can be shared if there are problems that require a joint analysis. | false | 64717 | 64440
64723 | Security Process requirements | Heading | [6 empty] | true | 64599 | 64440
64724 | Secure Development process | Heading | [6 empty] | true | 64723 | 64440
64725 | The contractor shall appoint a contact person responsible for the security risk management. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} |  |  | false | 64724 | 64440
64726 | The contractor shall provide detailed information in a format coordinated with the client with each software release regarding used FOSS. | Requirement | agreed | accepted | PM | 158978: FOSS Scan results {LINK id=130932.158978 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_qTyiARDMEe6kHpr-xdouxA} | 2021-12-07 CH: accepted | This shall be applicable only if FOSS is used. | false | 64724 | 64440
64726 | The contractor shall provide detailed information in a format coordinated with the client with each software release regarding used FOSS. | Requirement | agreed | accepted | PM | 158978: FOSS Scan results {LINK id=130932.158978 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_qTyiARDMEe6kHpr-xdouxA} | 2021-12-07 CH: accepted | This shall be applicable only if FOSS is used. | false | 64724 | 64440
64727 | The contractor shall provide detailed information in a format coordinated with the client regarding all software and hardware components used. | Requirement | partly agreed | accepted | PM | 154093: Security Bill of Materials {LINK id=130932.154093 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_-EJFkO12Ee2Aa7te25qZeg} | 220414ub: accepted 2022-02-03 CH: accepted? | Format to be clarified. | false | 64724 | 64440
64728 | The contractor shall disclose upon request all implemented security measures to the client. | Requirement | agreed | accepted | PM | 153663: Technical Customer Documentation {LINK id=130932.153663 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_0auLAumWEe2Bvr_BtPnMGg} | 211119ub |  | false | 64724 | 64440
64729 | Software components shall be distinguishable by uniquely identifiable software version. When using FOSS, the version numbers from the original source shall be taken over. For the adaptation of FOSS components, the deviation to the original template shall be documented and communicated to the client. | Requirement | agreed | accepted | PM | 154093: Security Bill of Materials {LINK id=130932.154093 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_-EJFkO12Ee2Aa7te25qZeg} | 2021-12-07 CH: accepted? kein FOSS, richtig? | Uniquely identifiable software versions can be provided. Further details to be discussed. No FOSS is used in IMU. | false | 64724 | 64440
64730 | If FOSS components are used, the underlying source code shall be available to the client when requested, if the corresponding FOSS-license permits this. | Requirement | agreed | accepted | PM | 158978: FOSS Scan results {LINK id=130932.158978 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_qTyiARDMEe6kHpr-xdouxA} | 2021-12-07 CH: accepted? kein FOSS, richtig? | No FOSS is used in IMU. | false | 64724 | 64440
64730 | If FOSS components are used, the underlying source code shall be available to the client when requested, if the corresponding FOSS-license permits this. | Requirement | agreed | accepted | PM | 158978: FOSS Scan results {LINK id=130932.158978 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_qTyiARDMEe6kHpr-xdouxA} | 2021-12-07 CH: accepted? kein FOSS, richtig? | No FOSS is used in IMU. | false | 64724 | 64440
64731 | On request the contractor shall confidentially make available information and documents about implementations on external interfaces (e.g. Bluetooth, Air-Interface), including protocols going through this interfaces and the relevant target applications, to the client for a security review. | Requirement | agreed | accepted | PM | 153663: Technical Customer Documentation {LINK id=130932.153663 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_0auLAumWEe2Bvr_BtPnMGg} |  |  | false | 64724 | 64440
64732 | The contractor shall provide the client with all needed documents and information about the deployed operation system, services and applications (concepts, design, API etc.). | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} | accepted | To be clarified in DIA. Which format are the documents needed and other time line details to be discussed. | false | 64724 | 64440
64733 | The contractor shall ensure that the product is only able to be changed by authorized developers and that all changes to the product are understandable at any time (when, who, what has been changed, etc.). | Requirement | agreed | accepted | PM | {LINK uri=https://inside-docupedia.bosch.com/confluence/display/PMT/Work+Requests+and+Work+Products+Traceability} |  |  | false | 64724 | 64440
64734 | The contractor shall define and apply "secure coding guidelines". These shall be approved by the client. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64724 | 64440
64735 | Data handling outside of control units | Heading | [6 empty] | true | 64723 | 64440
64736 | The contractor shall protect the data of the client against unauthorized access, misuse, loss, destruction or change. | Requirement | agreed | accepted | PM | 154534: Rahmenvertrag {LINK id=130932.154534 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_CSHxsu8TEe2Aa7te25qZeg} 155441: Data Protection and information Security Training {LINK id=130932.155441 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_FoQd4wBoEe6S65toj012sg} |  |  | false | 64735 | 64440
64737 | The security concept shall be approved by the client. The client reserves the right to check the security concept and its implementation. | Requirement | agreed | accepted | PM | 159150: Security Concept Reviewed {LINK id=159150 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_-A-Y4BPuEe6T-5sVNjW_BA} 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} |  |  | false | 64735 | 64440
64738 | Change to the security concept shall be communicated to the client in writing. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} 159150: Security Concept Reviewed {LINK id=159150 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_-A-Y4BPuEe6T-5sVNjW_BA} |  |  | false | 64735 | 64440
64739 | User data shall be protected and be used only for the intended purpose. | Requirement | agreed | accepted | PM | 155441: Data Protection and information Security Training {LINK id=130932.155441 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_FoQd4wBoEe6S65toj012sg} |  |  | false | 64735 | 64440
64740 | Data of different users shall be stored separately. | Requirement | not agreed | accepted |  |  | 2021-12-07 CH: accepted? | Not applicable for MMP2 | false | 64735 | 64440
64741 | Access to the client's data-base is only permitted after written approval. Access to client's data shall not be passed on to third parties. Subcontractors can only access the data-base as part of their contracting and only and after written approval by the client. In case of the subcontracting ends or the assigned employees leave the project or the subcontractor, access permissions shall be canceled accordingly | Requirement | agreed | accepted | PM | 155490: Security tools and process handling {LINK id=130932.155490 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_UXzHgQFEEe6S65toj012sg} |  |  | false | 64735 | 64440
64742 | The contractor shall inform the client immediately in case of information security or data breach and to coordinate the next steps. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} |  |  | false | 64735 | 64440
64743 | For the information transfer with the client's systems or at the locations of the client, the contractor shall follow the specifications from the Supplier Portal. | Requirement | agreed | accepted | PM | 155490: Security tools and process handling {LINK id=130932.155490 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_UXzHgQFEEe6S65toj012sg} |  |  | false | 64735 | 64440
64744 | The contractor is obligated to inform the client if third parties (insolvency, investigation, etc.) access to the data of the client. Furthermore, the contractor shall inform the accessing third party that the data belong to the client. | Requirement | agreed | accepted | PM | 154534: Rahmenvertrag {LINK id=130932.154534 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_CSHxsu8TEe2Aa7te25qZeg} |  |  | false | 64735 | 64440
64745 | The contractor is obliged to inform the employees and subcontractors with access to data centers of the client, about information security relevant topics. | Requirement | agreed | accepted | PM | 155441: Data Protection and information Security Training {LINK id=130932.155441 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_FoQd4wBoEe6S65toj012sg} |  |  | false | 64735 | 64440
64746 | The contractor shall ensure that the data of the client cannot be accessed by other customers. | Requirement | agreed | accepted | PM | 154534: Rahmenvertrag {LINK id=130932.154534 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_CSHxsu8TEe2Aa7te25qZeg} |  |  | false | 64735 | 64440
64747 | The contractor is obliged to further education all employees for information security regularly. | Requirement | agreed | accepted | PM | 155441: Data Protection and information Security Training {LINK id=130932.155441 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_FoQd4wBoEe6S65toj012sg} |  |  | false | 64735 | 64440
64748 | All data classified by the client as "secret" or "confidential" shall be protected by cryptographic measures. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64735 | 64440
64749 | Test data shall be removed from production grade components. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_ha7lMK5uEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64735 | 64440
64750 | The contractor shall retain the data of the client for two years after termination of the service contract. After the deadline, the data shall be deleted. Upon request from the client, an earlier deletion of the data shall be done by the contractor. | Requirement | agreed | accepted | PM | 154534: Rahmenvertrag {LINK id=130932.154534 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_CSHxsu8TEe2Aa7te25qZeg} |  |  | false | 64735 | 64440
64751 | Source code secuirty shall be validated using code analysis tools according to industry best practices. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_-sdBkLTcEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64735 | 64440
64752 | The contractor is obliged to use the specified security tool and the supplied crypto material (key / certificate) of the client. The used crypto material and Security Tool can be changed in the lifecycle of the control unit / project. The contractor shall be obliged to implement and confirm the update according to the client's specifications. | Requirement | agreed | accepted | PM | 155490: Security tools and process handling {LINK id=130932.155490 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_UXzHgQFEEe6S65toj012sg} | 211119ub |  | false | 64735 | 64440
64753 | The contractor agrees that all users which needs access to diagnosis certificates of the client, recorded in it's user repository, and have to apply for access to the certificates. The access rights are issued according to the principle of "least privilege". The contractor agrees to inform promptly about changes that affect this principle (change of role, termination of employment, etc.). | Requirement | agreed | accepted | PM | 155490: Security tools and process handling {LINK id=130932.155490 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_UXzHgQFEEe6S65toj012sg} 155441: Data Protection and information Security Training {LINK id=130932.155441 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_FoQd4wBoEe6S65toj012sg} |  |  | false | 64735 | 64440
64754 | The contractor shall ensure, that control units do not accept any date/time that is available before the production date. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_vqrCgK00Ee2gK6aOUnWmEA?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64735 | 64440
64755 | The contractor shall not store any passwords or secrets in plain text. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_qA4b0axUEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64735 | 64440
64756 | Risk management | Heading | [6 empty] | true | 64723 | 64440
64757 | The contractor is obliged to perform and document a complete risk analysis for the product to be developed (including the clients requirements specifications and contractors platforms). | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_Fikv4KxNEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} | 211119ub |  | false | 64756 | 64440
64758 | In particular, the contractor shall point out, privacy- and safety- threats that results from security compromises. | Requirement | agreed | accepted | Security | {LINK uri=https://rb-alm-06-p.de.bosch.com/rm/resources/BI_Fikv4KxNEeyFJfKsiNWFzw?oslc_config.context=https%3A%2F%2Frb-alm-06-p.de.bosch.com%2Frm%2Fcm%2Fstream%2F_hHt98Q5aEeayWuF486H6EQ} |  |  | false | 64756 | 64440
64759 | The contractor is obliged to check for security vulnerabilities ("CVEs") and to monitor them during the life cycle of the product. If a vulnerability is detected, the contractor shall inform the client immediately and discuss necessary mitigations. | Requirement | partly agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} | 2021-12-07 CH: accepted? | Passive Monitoring is supported. WP-08-XX to be referred in CIA | false | 64756 | 64440
64760 | Pen test | Heading | [6 empty] | true | 64723 | 64440
64761 | The contractor grants consent that the client may test the items supplied by the contractor (including but not limited to products, systems, hardware, software, data), or have these tested by third parties, for compliance with information technology security requirements, in particular by means of penetration tests. The tests are aimed at individual items or complete systems. The test may include accessing, and hence possibly reproducing and/or editing computer programs, including the source code or other data. This may include data that is not intended for the client and that is specially secured against unauthorized access. To the extent that such testing may violate the rights of third parties to the articles supplied by the contractor, the contractor hereby grants consent also in the name of and on behalf of these third parties. | Requirement | partly agreed | accepted | PM | 154126: Penetration Test Alignment {LINK id=130932.154126 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_q1Kycu16Ee2Aa7te25qZeg} | 2021-12-07 CH: accepted | As agreed in the SLA. | false | 64760 | 64440
64762 | The contractor is obliged to perform a penetration test. The penetration test shall include all component developed and deployed by the client. The result of the penetration test shall be provided to the client before C-sample phase. | Requirement | agreed | accepted | PM | 154126: Penetration Test Alignment {LINK id=130932.154126 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_q1Kycu16Ee2Aa7te25qZeg} | 2021-12-07 CH: accepted? | Refer to CIA/DIA WP-10-07. To be verified with the over all plan to know which software can be used to perform the penetration tests. | false | 64760 | 64440
64763 | The contractor is obliged to grant the client access to selected source code and related documents for security reviews by the client and by 3rd party companies assigned by the client. | Requirement | not agreed | accepted | PM |  | 220422ub: accepted, as defined in DIA 2021-12-07 CH: please set to "agreed"/"partly agreed" when commenting "to be clarified in DIA". DIA 8 weeks after project allocation. | View at location shall be made possible. To be discussed. Refer to CIA/DIA WP-10-01 WP-10-02. | false | 64760 | 64440
64764 | The contractor is required to provide the client or an commissioned third party with the source code as well as all necessary for an automated code scan (SCAS, Source code analysis service). | Requirement | not agreed | accepted | PM |  | 220422ub: accepted, as defined in DIA 2021-12-07 CH: please set to "agreed"/"partly agreed" when commenting "to be clariefied in DIA". DIA 8 weeks after project allocation. | View at location shall be made possible. To be discussed. Refer to CIA/DIA WP-10-01 WP-10-02 | false | 64760 | 64440
64765 | The contractor is obliged to contribute to partial source code analyses related to the part of the source code owned by the contractor. | Requirement | not agreed | accepted | PM |  | 220422ub: accepted 2021-12-07 CH: accepted? | View at location shall be made possible. To be discussed. Refer to CIA/DIA WP-10-01 WP-10-02 | false | 64760 | 64440
64766 | The contractor is obliged to assess the analyses’ outcomes in cooperation with the client and, if necessary, to discuss appropriate measures in cooperation with the client. | Requirement | agreed | accepted | PM | 154126: Penetration Test Alignment {LINK id=130932.154126 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/BI_q1Kycu16Ee2Aa7te25qZeg} |  |  | false | 64760 | 64440
64767 | Incident management | Heading | [6 empty] | true | 64723 | 64440
64768 | The contractor is obliged to inform the client of any known vulnerabilities of his products. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} |  |  | false | 64767 | 64440
64769 | The contractor is obliged to cooperate with the client to mitigate known vulnerabilities. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} |  |  | false | 64767 | 64440
64770 | The contractor is obliged to inform the client of vulnerabilities in any 3rd party software within the contractor’s products applied for the client. | Requirement | agreed | accepted | PM | 154829: CyberSecurity Interface Agreement {LINK id=154829 uri=https://rb-alm-08-p.de.bosch.com/rm/resources/TX_J4iuMPL9Ee2Aa7te25qZeg} | accepted | Vulnerabilities inside the SSA requires information exchange between client and contractor. | false | 64767 | 64440
64771 | Standard Software Architecture | Heading | [6 empty] | true | 64441 | 64440
METADATA
Exported Artifact IDs=64599¦64600¦64601¦64602¦64603¦64604¦64605¦64606¦64607¦64607¦64608¦64609¦64610¦64609¦64610¦64611¦64612¦64613¦64614¦64615¦64616¦64617¦64618¦64617¦64618¦64619¦64620¦64621¦64622¦64623¦64624¦64625¦64626¦64627¦64628¦64629¦64630¦64631¦64632¦64633¦64634¦64635¦64636¦64637¦64638¦64639¦64640¦64641¦64642¦64643¦64644¦64645¦64646¦64647¦64648¦64649¦64650¦64651¦64652¦64653¦64654¦64655¦64656¦64657¦64658¦64659¦64660¦64661¦64662¦64663¦64664¦64665¦64666¦64667¦64668¦64669¦64670¦64671¦64672¦64673¦64674¦64675¦64676¦64677¦64678¦64679¦64680¦64681¦64682¦64683¦64684¦64685¦64686¦64687¦64688¦64689¦64690¦64691¦64692¦64693¦64694¦64695¦64696¦64697¦64698¦64699¦64700¦64701¦64702¦64703¦64704¦64705¦64706¦64707¦64708¦64709¦64710¦64711¦64712¦64713¦64714¦64715¦64716¦64717¦64718¦64719¦64720¦64721¦64722¦64723¦64724¦64725¦64726¦64726¦64727¦64728¦64729¦64730¦64730¦64731¦64732¦64733¦64734¦64735¦64736¦64737¦64738¦64739¦64740¦64741¦64742¦64743¦64744¦64745¦64746¦64747¦64748¦64749¦64750¦64751¦64752¦64753¦64754¦64755¦64756¦64757¦64758¦64759¦64760¦64761¦64762¦64763¦64764¦64765¦64766¦64767¦64768¦64769¦64770¦64771
Export Project Area=https://rb-alm-08-p.de.bosch.com/rm/rm-projects/_WanoAKD9EeyqmKs83UZRFw/components/_AHQ-QKFLEeyqmKs83UZRFw
Export Configuration=https://rb-alm-08-p.de.bosch.com/rm/cm/stream/_AHavRqFLEeyqmKs83UZRFw
Export Locale=de
Export Module=https://rb-alm-08-p.de.bosch.com/rm/resources/MD_4ZnuZqFQEeyqmKs83UZRFw
Export Errors (listed in cells)=19